I recently talked with  general contractor and asked him to look at the app and give me his opinion and or any additions he might recommend. He laid it out the order that things happen in his line of work. He said that every detail has to be planned, contractors need to give their estimates for their scope of work and time frame, all materials (including every screw, nut bolt etc…) crews & employees, length of time for the project, permits and time to receive, and any other scope of the job that is needed. He said sometimes the quote can takes days to a week to put together. We need to design our estimates/quotes to be able to handle such things. They need to be able to save the added progress and help with reminders.

Here is what the research says that we need to have/build and the workflow:

Yep — GC is the “air traffic control” layer, and if you miss pieces you’ll feel it later (permits stuck, subs not insured, pay apps messy, schedule chaos, change orders untracked, lien exposure… the fun stuff 🙃).

Below is a GC-specific “don’t-miss-anything” blueprint you can turn directly into Sitesense modules, screens, and required fields. I’m basing this on common GC practices + widely used standards for submittals, progress billing/pay apps (AIA G702/G703 + Schedule of Values), closeout, CO/inspections, CPM scheduling, and lien waivers. (Learn - ACD Operations)

The GC Operating System (What Your App Must Cover)

Core modules a real GC needs (minimum viable “I can run a job”)

- CRM + Lead Intake

- Estimating + Bid Management

- Contracting (Owner + Subcontracts)

- Permits + Inspections + CO tracking

- Scheduling (Master + short-term)

- Procurement (materials, long-leads, submittals)

- Field Execution (daily reports, QA/QC, safety)

- Financials (SOV, pay apps, retainage, cost tracking)

- Change Orders

- Closeout (warranties, O&Ms, as-builts, lien releases) (Procore)

1) GC Workflow with Multiple Subcontractors (Phases → Tasks)

Phase A — Lead Intake & Precon Setup

Key tasks

- Capture scope: project type, size, address, owner, design team

- Site constraints: access, working hours, staging, neighbors, utilities

- Identify trades needed (bid packages)

Must-have fields

- Project delivery method (GC, design-build, CM)

- Bid due date, target start date, target substantial completion date

- Stakeholders: Owner, Architect/Engineer, inspectors, utility contacts

- Docs: plans, specs, photos, geotech (if any)

Phase B — Estimating & Bid Management (with Bid Packages)

GC estimating is basically: break scope into packages, invite subs, normalize bids, build SOV and quote.

Key tasks

- Build Bid Packages (by trade / CSI division)

- Send ITBs, manage RFIs during bidding, collect bids

- Level bids (apples-to-apples comparisons)

- Build detailed estimate + contingency + overhead/profit

- Produce proposal + inclusions/exclusions + alternates

Must-have fields

- Cost codes (ideally CSI MasterFormat based) for consistency (Procore)

- Estimate structure:

  - Line item, quantity, unit, unit cost, labor/material/equipment split

  - Allowances (owner selections)

  - Alternates (add/deduct)

  - Contingency

- Bid leveling:

  - Scope included/excluded

  - Assumptions, clarifications, lead time

  - License/insurance verification status

Output your system should generate

- Detailed quote + scope narrative

- Schedule of Values (SOV) draft (because it becomes billing later) (CSI Resources)

Phase C — Contracting (Owner Contract + Subcontracts)

Key tasks

- Owner agreement executed

- Build and execute subcontracts per trade with:

  - Scope, schedule, payment terms, retainage

  - Insurance requirements and compliance tracking

Must-have fields

- Contract value, retainage %, billing terms, payment milestones

- Subcontract scope (linked to bid package + SOV items)

- COI tracking, additional insured, waiver of subrogation, expirations (IRMI)

- Compliance checklist per sub before they can mobilize (license, W-9, safety plan if required)

Phase D — Permits, Inspections & Utility Coordination

This is where projects die slowly if you don’t track it.

Key tasks

- Determine permit types (building, electrical, plumbing, mechanical, demo, ROW, etc.)

- Submit permit set, track plan review comments, resubmittals

- Track required inspections and signoffs

- Track Certificate of Occupancy (CO) / final close permits (Procore)

Must-have fields

- Permit authority/jurisdiction, permit #, status, fees

- Inspection list with dates, results, corrections, reinspection date

- Dependencies (cannot drywall before rough inspections, etc.)

- CO required? Temporary CO? Conditions?

Phase E — Planning & Scheduling (Master + Lookahead)

Key tasks

- Create baseline schedule (CPM-ish structure for big jobs, simpler for small) (Smartsheet)

- Sequence trade work + inspections + long-lead procurement

- Weekly lookahead planning (what’s actually happening next week)

Must-have fields

- Milestones: mobilize, rough-in complete, drywall, substantial completion, final

- Activity dependencies + responsible party (GC/sub/vendor)

- Constraints log (permits pending, materials delayed, access issues)

- Schedule versioning + baseline vs current

Phase F — Submittals, Procurement & Long-Leads

Submittals are a real contract process (and a huge schedule driver). (Learn - ACD Operations)

Key tasks

- Create submittal register (from specs)

- Collect shop drawings/product data/samples

- GC review then submit to architect/engineer

- Track revisions/approvals and lead time

- Procure and track deliveries / material storage

Must-have fields

- Submittal ID, spec section / package, vendor, required-by date

- Status: Draft → Submitted → Revise & Resubmit → Approved

- Lead time + delivery ETA + “needed on site” date

- Attachments: shop drawings, cutsheets, test data, approvals (AIA Community Hub)

Phase G — Execution (Field Management)

Key tasks

- Daily reports (labor on site, weather, deliveries, work completed)

- RFIs (questions), field directives

- Quality checks & punch as you go

- Safety logs (incidents, toolbox talks if you want this later)

Must-have fields

- Daily log: date, weather, subs on site, headcount, activities, photos

- Issues list: blockers, decisions needed, owner selections pending

- QA/QC checklists by trade

- Punch list items (location, trade responsible, due date)

Phase H — Billing, Pay Apps, Retainage, and Lien Protection

This is the money engine. Many GCs bill using Schedule of Values + pay applications (AIA G702/G703 are common). (Learn - ACD Operations)

Key tasks

- Maintain Schedule of Values (SOV)

- Monthly pay app:

  - percent complete per line item

  - stored materials tracking

  - retainage calculation (Werx)

- Collect subcontractor invoices

- Collect lien waivers tied to each payment (Learn - ACD Operations)

Must-have fields

- SOV line items: original amount, approved COs, completed-to-date, retainage, balance

- Pay app period, billing through date, backup docs

- Sub pay tracking: invoice received, approved, paid, waiver collected

- Waiver types: conditional/unconditional progress/final (state rules vary) (Learn - ACD Operations)

Phase I — Change Orders (Owner + Sub)

You already have a CO workflow—good. For a GC, you need two linked layers:

- Owner Change Order (what owner approves & pays)

- Sub Change Orders (what subs charge you)

Key tasks

- Capture change request

- Get pricing from affected subs

- Add GC markup rules (OH&P) if applicable

- Get approval (signature)

- Update SOV + schedule + budget

Must-have fields

- CO ID, reason code, description, affected cost codes/SOV lines

- Cost breakdown + schedule impact

- Approval signatures + dates

- Link owner CO ↔ sub COs ↔ field tasks

Phase J — Closeout (Docs, CO/Final, Handover)

Closeout isn’t a “last week” thing — it’s ongoing document collection. (Autodesk)

Key tasks

- Final punch list close

- Collect:

  - warranties

  - as-builts/record drawings

  - O&M manuals

  - testing reports

  - final lien waivers/releases

  - permit signoffs and CO (Procore)

- Owner training + turnover package

Must-have fields

- Closeout checklist (by spec section / trade)

- Document collection status per subcontractor

- CO status and final inspection pass confirmations (Procore)

- Warranty start/end, contact, claim procedure

2) The “Don’t Miss Any Details” Data Model (GC Required Entities)

If your system has these entities, you’ll cover 95% of GC reality:

- Project

- Stakeholders (Owner, A/E, inspector, utilities)

- Bid Packages (trade scopes)

- Subcontractors + Compliance (license, insurance, COI expirations)

- Estimate (line items + cost codes + allowances + alternates)

- Schedule (milestones, activities, dependencies, constraints)

- Submittals (register + attachments + approvals)

- Procurement (POs, deliveries, long-leads)

- Daily Reports

- RFIs

- Issues / Decisions Log

- Inspections / Permits / CO

- SOV

- Pay Apps (with retainage + stored materials)

- Invoices (subs/vendors)

- Lien Waivers (progress/final; conditional/unconditional)

- Change Orders (owner + subs linked)

- Punch List

- Closeout Package (warranties/O&M/as-builts)

This structure maps directly to how pay apps (G702/G703 + SOV) work and how closeout documents get tracked. (Trimble)

3) What To Build First (So You Don’t Build a Monster That Eats You)

If you want “detailed quote + run the project” without drowning:

Phase 1 (Quote Engine)

- Bid packages + sub invites + bid leveling

- Estimating with cost codes

- Proposal output (scope + inclusions/exclusions + alternates)

- Generate initial SOV from estimate (same structure carries into billing) (CSI Resources)

Phase 2 (Run Engine)

- Schedule + constraints + inspections

- Submittals + procurement

- Daily reports + punch list

- Change orders (owner + subs linked)

Phase 3 (Money & Risk Engine)

- Pay apps + retainage

- Sub invoice approval

- Lien waivers and closeout doc enforcement (Learn - ACD Operations)

Next: I can package this into a downloadable “GC Industry ReadMe”

If you want, I’ll generate a downloadable file that includes:

- Full GC workflow (phases/tasks)

- Full required fields list (by module)

- Recommended screens

- Database field suggestions (tables + relationships)

- Example SOV structure + pay app fields + waiver tracking

Say PDF or Markdown, and whether you’re targeting residential, commercial, or both (it changes how heavy permitting/submittals/billing need to be).